## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Mar. 21-Apr. 1 | Week 2 Apr. 4-8 | Week 3 Apr. 11-15 | Week 4 Apr. 18-24 | Week 5 Apr. 25-29 | Week 6 Apr. 30-May. 3
UI Interface Implementation | 2 | 3 | 4 | 2 | 0 | 0
FileReader Class Implementation | 3 | 2.5 | 2.5 | 0 | 0 | 0
FileReader Test | 0 | 2 | 2 | 0 | 0 | 1
ChartSetter Class Implementation | 0 | 4 | 5 | 2 | 0 | 0
Task1 Implementation | 0 | 2 | 3.5 | 3 | 2 | 0.5
Task2 Implementation | 0 | 1 | 3.5 | 4 | 3 | 0.5
Task3 Implementation | 0 | 2 | 3 | 3.5 | 2.5 | 0.5
Task4 Implementation | 0 | 1 | 2.5 | 4 | 2 | 0.5
Task5 Implementation | 0 | 2 | 2 | 3.5 | 2.5 | 0
Task6 Implementation | 0 | 0 | 2.5 | 3 | 3 | 0.5
Task1&Task4 Test | 0 | 0 | 0 | 3 | 2.5 | 2
Task2&Task5 Test | 0 | 0 | 0 | 2 | 3 | 2.5
Task3&Task6 Test | 0 | 0 | 0 | 2.5 | 2 | 2
Total hours | 5 | 19.5 | 30.5 | 32.5 | 22.5 | 10
Left Hours | 115 | 95.5 | 65 | 32.5 | 10 | 0